## Slide 1: CAB 2027-2029 Strategic Plan Development Project
August 21st, 2026

## Slide 2: Update
Update on responses to:
  Stakeholder survey
  Staff survey
  Client survey and interviews
Updated timeline

## Slide 3: Survey Response Update
Stakeholder Survey: 6 responses
Staff Survey: 55 responses
Client Survey: 364 responses and 5 Client interviews

## Slide 4: Updated Timeline
HRSA Electronic Handbooks (EHBs) Documentation
Timeframe | Activity | CAB Input
Early August 2026 | Client surveys sent to: patients with activated “My Chart” – 8,279 Staff – 124 County, 252 UCD Stakeholders - 65 | 
Late August | SWOT findings analyzed. Themes and priorities drafted by group and aggregate. Complete Environmental Scan. Gather and summarize patient data. | Provide SWOT findings, themes and priorities to CAB.
September 2026 | Develop strategic priorities, draft goals and activities. Complete interviews, focus groups, or other data gathering methods. | Preliminary information presented to CAB
September/October 2026 | Draft themes, goals and activities. Begin development of metrics, and targets. Begin comparative analysis to previous data. | Plan update to CAB.

## Slide 5: Updated Timeline
Timeframe | Activity | CAB Input
October 2026 | Prepare introduction, methods, needs assessment summary, patient population overview, and environmental scan components. | CAB reviews draft sections and provides feedback
Early November 2026 | Finalize themes, goals and activities. Finalize outcome measures. Incorporate CAB revisions, finalize outcome measures and implementation/activity components. Create Plan design and begin designing completed sections. Provide complete Plan to CAB for review (early November). | Draft Plan to CAB
Late November 2026 | Incorporate CAB review (late November). Final preparation of approval packet; final edits and formatting. | Review final pre‑approval materials
December 2026 | Final CAB approval of Strategic Plan | Formal vote

## Slide 6: Questions